## Sheet1
Req # | Requirement Details | ProductionStatus: Deployed / In-progress
1 | Permissions only requested by app when any particular service is to be used by Consumer | Deployed
2 | Country Code Seletion and Search implemented | Deployed
3 | Country Flag Integrated | Deployed
4 | Integration of R&R functionality with Shop N Drop | Deployed
5 | Service charges message prompt (Rs200 & $6) | Deployed
6 | Customer Profile country code will also have country flag | Deployed
7 | Reject Reasons with Rider's interaction flows (Photo and price rejections scenarios) | Deployed
8 | G+ issue on Registration issue Fix | Deployed
9 | Tell a Friend Button | Deployed
10 | Report for Cash reconciliation required to be sent on daily basis on the shared format. | In-progress
11 | MyRider billing rules updates. Please implement the following rules regarding pricing/service charge. Also fix the following items in rider credit report. 1. If payment mode is credit card than service charge should be PKR 200 plus 2.5% of item price (to be calculated automatically) 2. If item price is greater than PKR 5000, then COD should be disabled (due to high risk of non-collection). Only credit card option should be enabled. In future, Jazz cash or sim sim etc can be enabled also. Also note that the riders do not have more than PKR 5000 cash in hand hence money will have to be sent from HO to those riders doing tasks for value greater than PKR 5000. | In-progress
12 | MyRider tasks are priority and should be in Red color on Provider app | In-progress
13 | Rider should have the functionality to disable “Cash on Delivery” | In-progress
14 | Riders should be given the functionality to set Peak Factor (2x Cost) for special tasks with separate delivery and cash receiving rides | In-progress
15 | Rider’s should be given the functionality to create a task from the provider app which would be auto assigned to them. For catering similar requests on spot. | In-progress
16 | Scenario’s discussed : 1. Customer wants to pay not by credit and is in another city. 2. Customer wants to pay not by credit and is in another city in Pakistan etc. | In-progress
17 | Device Serial number column needs to be removed from the “Repair & Return” interface on the dashboard. | In-progress
18 | STC number to be removed from second step of MyRider R&R and from the task description step | In-progress
19 | Jazz -> BVS Repair . R&R requests to be placed in Jazz filter on dashboard with category/Type name as "BVS Repair" | In-progress
20 | Photo capture of accessories taken should be mandatory and should auto appear after accessories select flow. The manual picture take button should be disabled for R&R. Also the picture taken should go to dashboard for this task. Also this task tabular interface should be improved | In-progress
21 | Invoice should not appear on Rider side or consumer side for R&R tasks. Currently showing on Provider side. | In-progress
22 | IMEI scan feature to incorporate at iOS consumer side as well. | In-progress
23 | IMEI barcode scanning is taking some time to pick numeric values from bar code. Needs enhancenment | In-progress
24 | On Dev environment for R&R the request is now easily being created for MSISDN / IMEI values other than the inventory data. Please check and resolve this issue | In-progress
25 | “Already registered go back & sign in” message box should appear, if the user is already registered. (Need to have this text in the error message) | In-progress
26 | There should be a message box instead of Toast message on Provider application or perhaps a ticker that displays recent message such as rejection of item photo. (Cancellation reasons are appearing but the message dialog should also appear for all other response messages to Provider app) | In-progress
27 | Receipt on Rider application should be developed to give an authentic look for customer on delivery. | In-progress
28 | Customized MyRider Provider reasons of cancellation | In-progress
29 | Rider’s Provider app messages should be in dialog boxes to improve operations. | In-progress
30 | Please add transaction ID inside History interface for that Item and on the Invoice interface at the end before rating in the consumer application for Credit Card payment method. | In-progress
31 | Look into feasibility from changing current PHP implementation of MyRider to Java especially in terms of optimization. | In-progress
32 | Request time should be integrated based on Average time from current request location wise data. A message should appear on creation or rider assignment that “your order will be catered within _______ minutes approximately” / “activity on your order will started in ______ minutes approximately”. (Try choosing rider with least time to reach and perform task) | In-progress
33 | “Click to Order” instead of “Shop N’ Drop” | In-progress
34 | High value transactions process needs improvement. | In-progress
35 | There can be two way or three way rides for a task and process needs to be improved for N-way rides for example 4 trips on one task (like collecting 3 books of same author from a publisher and distributing them amongst 3 friends in one city but different locations) | In-progress
36 | Pricing need to be revised based on request channel and nature of task. | In-progress
37 | Need to discuss whether the Dispatcher role must be merged with Finance role. That is, a Dispatcher in each region has some special privileges and some process for issuing and receiving large amount of cash for high valued tasks and what will be the process of submitting to finance department of STC and similarly for reporting/operations (should the dispatcher have a separate bank account). | In-progress
38 | It was decided in meeting to keep TAT below 36 hours for heavy cash handling tasks and what will be the process of handling cash by riders and need to figure out fail over scenario for riders performing large cash handling tasks. | In-progress
39 | It was decided to generate SMS to regional Dispatcher if any task is not assigned by dispatcher within 15 minutes. In addition to 11th item , if any particular request / task is still not assigned any rider by regional dispatcher within 45 minutes than a SMS for escalation will be auto generated to MSISDN of Sir Waqas Khan and Sir Umer Moeen simultaneously. | In-progress
40 | Role based Dashboard implementation like finance, Dispatcher should be performing tasks only relevant to their scope and the buttons that are not concerned to their flow should be hidden and STC information should be protected. | In-progress
41 | On Dashboard the dispatcher should receive notification of request being created from iOS and Android. The notification on dispatcher portal for a task should be disabled if that task has been catered by another dispatcher of the same region. | In-progress
42 | If some Rider is caught in a queue for catering any task then based on SOP the rider may cancel a task and select a reason relevant to this scenario. | In-progress
43 | STC-Dev to share demographic details of My Rider usage in different regions of Pakistan. Based on the demographical analysis and demand a marketing campaign will be launched using SMS. On the SMS a link for each platform should be available for downloading the app from Android and iOS. Link face text should also be short. | In-progress
44 | STC-Dev to branch current code for new implementation and to lock as well as store the current working My Rider apps versions. | In-progress
45 | Higher management will decide on how to handle Bill payment categories and process through My Rider service. | In-progress
46 | There should be separate reports for dashboard on registered users and different reports should be generated for iOS and Android users. | In-progress
47 | Find total footprint of My Rider | In-progress
48 | If waiting time for tasks from riders is more than 30 minutes then the charges should be increased. | In-progress
49 | On rating add waiting charges if the wait activity was after acceptance of price but on drop location. Flow needs to be discussed and enhanced. | In-progress
50 | SMS waiting charges to customer if riders is waiting on some activity. | In-progress
51 | UBL Tax to be checked in case of credit card payments. | In-progress
52 | After 12 pm orders should be created but an SMS should be generated to customer that the task can be performed in day time only. Improve and discuss flow. | In-progress
53 | Decided to keep Bill and Queues as separate category of button on My Rider main menu. | In-progress
54 | Instead of Pick and Drop, Collect & Deliver should be displayed and this will be a two way trip by rider and charges for two trips. | In-progress
55 | Shop N Drop should have separate billing flow and report. | In-progress
56 | For two way trip base charges Rs. 300. Pick location and drop locations should be displayed separately on consumer apps. | In-progress
57 | Enhancement : on new version available the consumer application should prompt new version available for update along with a notification and in settings so that the user may update when required. | In-progress
58 | Contacts access permission in Android / iOS consumer app should be removed, it is not required. | In-progress
59 | To discuss whether to take MyRider services on cloud or keep it in the current server setup/architecture. | In-progress
60 | Remove all permission request messages from the starting interface of the MyRider Consumer application. | Deployed
61 | Addition of search functionality on the country code selectable input field on registration. | Deployed
62 | City should be changed to “Select City”. | Deployed
63 | Zip code input text box should be retained but should not be mandatory. | Deployed
64 | In one of the dialog boxes probably the PIN interface where there is a message that “Sms will be sent” we have to fix the text from “Sms” “SMS”. | Deployed
65 | Sahiwal is missing from the list of cities where MyRider service is available. | Deployed
66 | Forget Password should be numeric 6 digits instead of alphanumeric, currently too much complex for users. | Deployed
67 | Create Request time should be reduced. This is the time when create request is tapped. | Deployed
68 | Timing also needs to be improved for status updates on notification screen of Item delivery / rider activity. | Deployed
69 | Kindly add reason for rejection of photo by customer in consumer application. Preferred to have radio buttons as option if customer rejects. | Deployed
70 | Reason of rejection for price Accept / Reject screen on consumer application. Sample messages are as follows: •Too Expensive •Look for another option •My Budget is within _________. This option if selected should open an input text box for the user to share budget for purchasing the item. Value should be sent to Provider application. •Please look for the item from a separate location ___________. Again this value should be provided by customer •Please resend me the photo it is blurred. •Please resend me the photo of my product the shared picture is wrong item •I would like ___________ . For the customer to add any information if the above don’t apply | Deployed
71 | Job Completion SMS should be enabled. | Deployed
72 | Implementation of two-way verification by using MSISDN and SMS, not email. This will involve sending code on MSISDN and then entering that code for registration. | Deployed
73 | Customer add to credit flow should also be thought of for managing cash at hand “change” issues. Adding to next item if change not available. In this case, Undertaking should include a line for customer to get the exact cash amount ready on delivery and it is his/her responsibility to do so. | Deployed
74 | Pictures/Gallery access permission in Android / iOS consumer app should be prompted only when the customer is entering or updating that information. Like if he wants to update his profile picture only then request access so that if the customer is willing he/she would allow otherwise go with the current flow. | Deployed
75 | Task pictures from riders must be stored on the web server / cloud and not on the consumer’s application for Android / iOS. (Already working in current flow) | Deployed
76 | Kindly do not make application updates mandatory for any user in production. There should be backward compatibility of our apps and services. Older versions must be functional and should not stop at any cost. | Deployed
77 | Reports required from MyRider database: Services, daily (24hrs) signed-up users, their first name / last name / Total number of consumers so far . | Deployed
78 | Validation of Password is also requires an icon just like in the case of mandatory fields “information icons”, should have information to enter 6 digits at least. | Deployed
79 | Scrollable Registration interface required on Android and iOS. | Deployed
80 | Forget password is not working. To check in production what caused this issue and whether it is the case with social media login-for which password is not required or the actually for manual login. | Deployed